## Slide 1
Tax Service Development – Managed Service

## Slide 2
TEKSYSTEMS | AGENDA
Slide Information | Slide Number
Scope | 3
Onboarding Plan | 4
Work Process | 5
Full Stack Engineering Team – India | 6
MEWS Team | 7
Project Governance Communication Plans | 8
Sample Project Performance Metrics | 9
Engagement Logistics | 10
Q&A | 11

## Slide 3
TEKSYSTEMS | SCOPE
SOW
Work Description
- Full Stack Engineering Team
- Participate and deliver per SDLC
- Provide technical and solution guidance
- Perform all operations in AGILE methodology
- Provide metrics and data on an agreed
upon schedule
Service Functions
- Tax Manager Service
- Web UI for Tax Manager
- Tax Calculation Service
- Test Utility for Tax Calculator
- JSON Tax Rules Schema
Project Plan and Phased Approach
- Phase 0 – Setup
- Phase 1 – Tax Manager Service and Web UI Development
- Phase 2 – Tax Calculator service and Test Utility Development
Other activities
- RACI matrix
- Engagement Management
- Organization Structure
- Training and Compliance
- Artifacts and Data
- Assumptions & Dependencies, Risks, Schedule

## Slide 4
TEKSYSTEMS | ONBOARDING PLAN
TIMELINES
Timeline | Activity | Status Update
02/10/2025 to 02/14/2025 | SOW Signature and Contract Execution Initial kick-off with business Get resources confirmed | 
02/17/2025 to 02/28/2025 | Finalize all resources Introduce the team to MEWS Establish initial project level meeting with MEWS Get hardware and software requirements completed Resolve pending open items and have all things in place Start the cadence for Sprint execution Plan AGILE and JIRA structures with MEWS Setup project level meetings (DSU’s, bi-weekly meetings, weekly cadence….) | 
03/03/2025 to 03/07/2025 | Begin Sprint 1 with a good backlog Development work to begin | 
03/10/2025 to 03/14/2025 | Ensure entire team is up and running and open positions are fulfilled Monitor sprint execution and cadence and ensure any impediments are removed Create initial version of metrics and review with MEWS | 
03/17/2025 to 03/21/2025 | Ensure things run in seamless mode Create first version of metrics for sprints Retrospectives and other post sprint related AGILE ceremonies | 

## Slide 5
TEKSYSTEMS | WORK PROCESS
Risk | Mitigation Plan
Delay in Sprint delivery | Retrospectives from every sprint, understand issues and take corrective actions
Resource availability | Emergency issues may arise, we need to have other resources be able to pick the work
Over committing v/s under committing | Analyze on a sprint-by-sprint basis, and take corrective actions
Infrastructure related issues | Work with client to minimize delays and enable smooth working across shores
Scope Changes | Ensure scope is discussed, finalized and warranted changes are accepted during middle of sprints
Communication protocols | Ensure there is direct communication with client, internal resources and others
Implementing outcomes from sprint retrospectives | Ensure there is at least one item from each retrospective that is addressed with proper planning in forthcoming sprints, add on to the improvement areas sprint on sprint
Availability of MEWS SMEs to perform various functions | Ensure there is adequate UAT at the end of each sprint, ensure there is complete sign-off from MEWS point contact before moving on to next sprint.
Risks and Mitigation Plan

## Slide 6
TEKSYSTEMS | FULL STACK ENGINEERING TEAM – US/CANADA/INDIA
Role | Contact | Location | Tentative onboarding date | Work Hours (Monday to Friday) | Function
Senior Engagement Manager (1) | NandaGopal MastiRamamurthy (Nanda Masti) (nmastiramam@teksystems.com) | Dallas, TX, USA | 2/17/2025 | 7 AM CST to 4 PM CST | Onshore SPOC / Sr. EM
Senior Technical Services Manager (1) | Sandhya Subramanyam (ssubramanyam@teksystems.com) | India | 2/17/2025 | 10 AM – 8 PM IST | Offshore SPOC / Sr. TSM
Practice Architect (1) | Jean-Philippe Leblanc (jleblanc@teksystems.com) | Remote / Canada / USA | 2/17/2025 | 7 AM CST to 4 PM CST | Onshore Practice Architect
Business Analyst (1) | Sivakumari Bayapureddy (sbayapur@teksystems.com) | India | 2/17/2025 | 2.30 PM – 10.30 PM IST | Offshore Business Analyst
Lead Developer (1) | Rob Myers (bobmyers@teksystems.com) | Remote / Canada / USA | 2/17/2025 | 7 AM CST to 4 PM CST | Onshore Lead Dev
Architect/ Senior Lead Dev (1) | Saurov Thakur (sauthakur@teksystems.com) | India | 2/17/2025 | 2.30 PM – 10.30 PM IST | Offshore Architect / Senior Lead Dev
Senior Developer (2) | 1st Dev - Ooha Rani , 2nd Dev - TBD | India | 1st Dev – 2/17/2025 2nd Dev - TBD | 2.30 PM – 10.30 PM IST | Offshore Developers
SDET | K Sireesha (ksireesha@teksystems.com) | India | 2/17/2025 | 2.30 PM – 10.30 PM IST | Offshore SDET (QA)
Scrum Master | Priyadarshan Patnaik (ppatnaik@teksystems.com) | India | 2/17/2025 | 2.30 PM – 10.30 PM IST | Offshore Scrum Master

## Slide 7
TEKSYSTEMS | MEWS TEAM
Role | Contact | Location | Work Hours (Monday to Friday) | Function

## Slide 8
TEKSYSTEMS | PROJECT GOVERNANCE COMMUNICATION PLAN
Type of Communication | Audience | Frequency | Medium | Purpose | Responsibility
Project Kick-off | Key Stakeholders Project Owners Project Team | One Time | Teams | Executive Overview of Project Confirm understanding of project schedule, scope and objectives. | TGS : Mews:
Weekly Status Report | Project Owners Project Team | Weekly | Email | Review progress against plan. Plan work and deliverables. Resolve issues to keep project on track. | TGS : Mews:
Team Meetings | Project Team members (as required) | Daily as Needed | Teams | Address outstanding issues as they arise | TGS : Mews:
Leadership Team Status Meetings | Key Stakeholders Project Owners | Monthly/Quarterly as agreed | Teams | Review project accomplishments, decisions, pending and potential challenges | TGS : Mews:

## Slide 9
TEKSYSTEMS | SAMPLE PROJECT PERFORMANCE METRICS
Work Item: | Month work Delivered
TEK Total Stories * | 
TEK Total Other items* | 
TEK Total Defects | 
TEK Totals | 
Monthly TEK Average | 
Total TEK Work Delivered
Work Item: | Month work Delivered
TEK Total Story Points * | 
Monthly TEK Average | 
Total TEK Story Points
Work Item: | Month
Average Monthly Headcount | 
Average TEK headcount
Resource Updates: None
Performance Updates: None
Risks/Issues Captured:
Initiatives (RAG): Green
Resource Output: MoM
225 (November)
143 (December)
Rolling Throughput Percentage: 16.05%

## Slide 10
TEKSYSTEMS | ENGAGEMENT LOGISTICS
Item | Contact
Softwares and tools | MEWS
Access permissions / Security | MEWS
Hardware Infrastructure | TEK/MEWS
Hardware and Software
Trackers
Work Tracker | Cadence
Weekly Status Reports | Weekly
Sprint Reports | At the end of every sprint
Client Business Review | Monthly
PTO tracker | Bi-weekly
Leadership Meeting Cadence
Item | Contact | Frequency
MEWS Designated point contact and TEK | MEWS technical manager Nanda Masti & Sandhya S | Bi-Weekly (30 minutes)
TEK internal leadership meeting | Nanda Masti and Sandhya S | Daily (15 minutes)
Team meetings with TEK contacts | Nanda Masti, Sandhya S and TEK Team | Weekly (15 minutes)

## Slide 11
THANK YOU